|  | Water Quality Management and Remediation | Assessment and Management of Agricultural Drought | Soil-Water-Plant Interactions | Sustainable Use of Ground Water Resources | Use of Modern Tools in Water Management |
| --- | --- | --- | --- | --- | --- |
| Charge | Conduct an India-US Joint Workshop August 2006. Follow up activities would include offering technical training on water quality management and remediation. | Identification of U.S. universities/institutions in April 2006. Conduct an India-US Joint Workshop in August 2006. Facilitate graduate student training on drought assessment and management. | Conduct an India-US Joint Workshop in August 2006. Dispatch a U.S. expert assessment team visit to India to determine research collaboration needs. Based on the initial U.S. team visit to India, provide follow-up soil and water research study tours and faculty exchanges. | Conduct an India-US Joint Workshop in August 2006. USAID project 1- Resource-Conserving Agricultural Technologies USAID project 2 - Water-Energy Management (WENEXA) | Conduct an India-US Joint Workshop in August 2006. Organize bilateral pilot research for rural areas on selected modern technologies for water management. |
| Responsible U.S. entity | USDA/FAS in partnership with Private Sector, Land-Grant Universities and USDA/CSREES | USDA/FAS in partnership with USDA/CSREES and Land-Grant Universities | USDA/FAS in partnership with USDA/CSREES and Land-Grant Universities | USDA/FAS in partnership with USGS, USDA/ARS, USDA/CSREES and Land-Grant Universities | USDA/FAS in partnership with Private Sector, Land-Grant Universities and USDA/CSREES |
| Contact person-U.S. | Dr. Sylvana Li sylvana.li@usda.gov 202-690-2868 | Dr. Sylvana Li sylvana.li@usda.gov 202-690-2868 | Dr. Sylvana Li sylvana.li@usda.gov 202-690-2868 | USDA – Dr. Sylvana Li sylvana.li@usda.gov 202-690-2868 USAID - Larry Paulson: +91-2419-8217; Chinmaya Acharya: +91-2419-8274 | Dr. Sylvana Li sylvana.li@usda.gov 202-690-2868 |
| Responsible India entity | ICAR/DARE in partnership with CCS HAU Hissar CGWB/SGWD, CIBA, Chennai, CIFA, Bhub, CIFE Mumbai, CPCB, CPCB, Delhi,CSSRI, Karnal, IARI, Delhi, IIT Delhi, IIT Kgp, PAU, Ludhiana | ICAR/DARE in partnership with All WTC’s, ANGARU, CAZRI, CRIDA, Hyderabad, HAU, Hisar, IARI,ICAR, IGKV, IIT Mumbai, JNKVV,PAU, RCER | ICAR/DARE in partnership with ANGARAU, CRIDA, GBPUAT, HAU, IARI, IISS, PAU, Ludhiana ICAR/DARE in partnership with ANGARAU, CRIDA, GBPUAT, HAU, IARI, IISS, PAU, Ludhiana | ICAR/DARE in partnership with CGWB, All WTCs, HAU, Hissar, PAU, Ludhiana, MPAUT, Udaipur, GBPAUT, Pantnagar, WTCER, Bhubneshwar | ICAR/DARE in partnership with All WTCs, CRIDA, CSWRCTI, GAU, Navsari, ICARRCER, IIT Kharagpur MPAU Rahuri, WTC, Dehli |
| Contact person-India | Dr. J.S. Samra 91 011 25848364 jssamra@icar.org.in | Dr. J.S. Samra 91 011 25848364 jssamra@icar.org.in | Dr. J.S. Samra 91 011 25848364 jssamra@icar.org.in | Dr. J.S. Samra 91 011 25848364 jssamra@icar.org.in | Dr. J.S. Samra 91 011 25848364 jssamra@icar.org.in |
| Activity Description | Finalize the technical program and funding for water quality management and remediation during the Indo-U.S. joint workshop in late 2006. Training topics include surface water and groundwater quality monitoring with a focus on agricultural related non-point source pollution. | Finalize the technical program and funding for management of agricultural drought during the Indo-U.S. joint workshop in late 2006 Facilitate graduate student training on drought early warning and crop condition assessment techniques using agro-meteorological information and environmental satellites. | Finalize the technical program and funding for soil-water-plant interaction during the Indo-U.S. joint workshop in late 2006. Soil and water research study tours will be conducted for Indian scientists to learn U.S. technologies and best practices. In addition, facilitate US-India faculty exchanges. The goal is to have Indian and U.S. technical experts working together and develop a three year collaborative research plan. | Finalize the technical program and funding for sustainable use of ground water resource during the Indo-U.S. joint workshop in late 2006 USAID project 1- To promote efficient use of farm input resources through technologies through 0 till, raised and laser leveling technologies in the Indus-Ganges basin and southern India foster adoption of water conserving technologies USAID project 2 - To demonstrate water conservation technology (drip irrigation) that conserves water and power, as a resource management initiative and promoting effective water and energy management policy at state level | Finalize the technical program and funding for use of modern tools in water management during the Indo-U.S. joint workshop in late 2006 Provide rural populations with access to clean water by conducting pilot research of small-scale water and wastewater treatment systems. Other related topics include: watershed management related to fertilizer and pesticide applications, and irrigation efficiency and water saving techniques. |
| Timeline | Workshop completed by late 2006. Technical trainings to start end of 2006 and continue through 2007 and 2008. | Workshop completed by late 2006. Graduate student trainings through 2007 and 2008. | Workshop completed by late 2006. Study tour and faculty exchanges conducted as soon as possible. | Workshop completed by late 2006. USAID project 1 - September 2006 to September 2007 USAID project 2 - July 04- September 08 | Workshop completed by late 2006. Initiate the pilot research through 2007 and 2008. |
| Anticipated Start date | September, 2006 | September, 2006 | September, 2006 | USAID project 1 - September 2006 USAID project 2 - Already started | September, 2006 |
| U.S. Budget | USDA FY06 $132,000 | USDA FY06 $66,000 | USDA FY06 $66,000 | USDA FY06 $4,000 USAID FY06 P1-$500,000; P2-$900,000 | USDA FY06 $132,000 |
| Tentative India Budget | Matching budget as envisaged under the approved work plan for this activity exists as per need. |
| TOTAL BUDGET |  |  |  |  |  |